Python from Zero

A practical programming course for public-school teachers

Programme dossier

Prepared for Fast Foundation

| Structure | Two courses, one per school grade. Each is a practical Part 1 of 2 months and a theoretical Part 2 of 4 months that runs only if its Part 1 succeeds. Sections 1–10 describe the grade-10 course's Part 1; section 11 describes the grade-11 course's Part 1. Both are built and verified. |
| --- | --- |
| Part 1 format | 18 sessions × 75 minutes = 22½ hours, twice a week over nine weeks, plus homework between sessions; a midpoint and a final assessment, being redesigned |
| Delivery | Fully remote, over Google Meet with screen sharing. No session is held on site, in either course |
| Audience | Public-school teachers, any subject. No prior programming assumed — the course begins with installing software |
| Group size | 4–8 per group, one instructor |
| Deliverable | A runnable three-file Python program over the participant's own class data, demonstrated to a colleague |
| Cost | Zero. All software is free; nothing touches a paid service or needs the internet after session 1 |
| Judged by | Can they code? A teacher passes with more than 85% of tasks done; the course succeeds if more than 80% of teachers pass, and fails under 70% (section 8). Plus trial lessons with real pupils: one or two coding lessons in Part 1, two on theoretical material in Part 2. Part 2 is judged against teachers who already teach in a school (section 12) |
| Status | Both Part 1 courses are complete and verified. Neither has been taught to a cohort. Both Part 2s are visions |
| Version | 3.6 — for partner review · 16 October 2026 |

How to read this Sections 1–10 describe the grade-10 course — the method, the schedule, the curriculum, the expected results and the assessment. The method is shared by both courses, so section 3 is worth reading whichever one interests you. Section 11 is the grade-11 course in full — its own curriculum, schedule, assessment and deliverable, and what it assumes a teacher already knows on its first day. Section 8 sets out how the programme will be judged, including the one measurement that tests its central assumption. Section 9 sets out the one risk that matters — that teachers still do not feel comfortable coding after Part 1 — and how the course watches for it.

# 1.  Executive summary

A programme for public-school teachers who have never written a line of code. It is now two courses — one preparing a teacher for grade 10, one for grade 11 — and each is a practical Part 1 of two months followed by a theoretical Part 2 of four. This dossier describes the grade-10 course's Part 1; section 11 is the grade-11 course in full, which is also built. Part 1 is eighteen sessions of 75 minutes, twice a week for nine weeks, taught remotely in groups of four to eight. Every participant finishes with a small program they wrote themselves and can use: a gradebook that opens their own class list, shows who has passed, calculates the average, and saves changes back to a file.

The programme is deliberately unusual. Two years of conventional teaching has not produced teachers who can write a program. Our diagnosis is that the bottleneck is not missing theory but missing coding fluency — teaching through algorithmic problems asks beginners to work out what a program should do and how to write it at once, so they fail at both. This course separates the two loads: mechanics to fluency first, with almost no theory and no algorithmic difficulty, leaving problem-solving to a later course.

What we are asking you to evaluate Part 1 is a two-month experiment with a decision at the end, not a finished methodology. It is built and verified. Part 2 — the four months that follow — is a vision that runs only if Part 1 succeeds (section 12). Part 1 is judged on one question — can they code? The thresholds were agreed with you on 15 October and are in section 8.

# 2.  The problem this programme addresses

The fundamental problem is that the teachers cannot code. Not that they do not understand recursion, and not that they have not practised enough algorithms. They cannot comfortably produce working code at all — the typing, the syntax, the loop that runs, the error message that gets read and fixed.

When a course then teaches through algorithmic tasks, two things must happen at once: working out what the program should do, and working out how to write it. They are overloaded, they confuse the two, and they fail at both. A teacher stuck on an algorithm cannot tell whether they are stuck on the idea or on a missing colon. The theory never connects to the practice, because there is no practice for it to connect to.

Adding more theory does not help, because theory is not the bottleneck. Adding harder problems makes it worse.

## The bet

The programme in one sentence Teach coding first and algorithms later — not the other way round.

For two months: almost no theory — around 12 minutes of explanation per session, then 30 minutes of typing. No algorithmic difficulty whatsoever; nothing requires working anything out. A great deal of very simple code, all of it about the participant's own classroom. Concepts arrive as relief, never as definitions.

The intended sequence is: write code mechanically → concepts become obvious, because each one removes a difficulty just met → coding stops needing conscious attention → algorithmic problems become learnable. That last stage is not part of this course. It is the next one, if this works.

# 3.  Methodology — how the course teaches

Teachers are given a real classroom task, solve it with what they already know, and then — in the same session — meet the tool that collapses it. We call these discovery sessions; there are five.

| Topic | The real task | The long way they do it first | The tool, same session |
| --- | --- | --- | --- |
| 6 | A register for the whole class | One variable per student | Lists |
| 8 | Find one student's grade by name | Two parallel lists, read by hand | Dictionaries |
| 11 | Mark the whole class pass or fail | One if block per student | `for` loops |
| 17 | An average on every report card | The same six lines, four times | Functions |
| 22 | Keep the register after closing it | Retyping it every time | Files |

## A worked example — topic 6

Participants are told: a teacher needs somewhere to keep the whole class — every name, every score — so the program can work with all of them. With what they know by topic 6, that means one variable per student. The notebook supplies twenty; they add a few of their own and update the scores. It works, and it takes a while.

Thirty minutes later, in the same session, the list arrives and the whole register becomes two lines. The notebook puts the two versions side by side: 40 lines against 2. Nobody has to explain why lists are useful — the participants spent twenty minutes finding out, and got the answer before they went home.

## Three rules that make it work

| Rule | Why, and what it costs us |
| --- | --- |
| The relief comes in the same session. Always. | An earlier draft planted a difficulty in topic 6 and resolved it four sessions later. Good structure on paper, bad teaching in practice: adults who spend an evening on tedious work and go home with no resolution do not come back. If a session runs long, the optional tasks are cut — never the second half |
| The task is real, and the tedium is never named. | Participants are never told they are doing something in order to struggle. They are building a class register because a teacher needs one — which is true. Work you chose to do, and were then shown a better way to do, is a lesson; the same work revealed afterwards as a deliberate ordeal is a trick, and this audience has been let down enough already |
| The shortcut is promised in advance, in writing. | A participant who knows a shortcut is twenty minutes away types the long version willingly; one who does not starts wondering whether the course knows what it is doing |

Three smaller decisions follow from the same thinking. Every example is a classroom — students, grades, attendance, report lines — so a participant sees their Tuesday morning in any line of the course. Armenian explains and English codes: a teacher who names a variable in Armenian writes valid Python and can then read no other Python, search for no answer online and copy no example ever again. And every session contains one deliberate error, read together, because beginners lose more time to fear of red text than to any concept here.

# 4.  Schedule

18 sessions, twice a week over nine weeks. Sessions run 75 minutes. Every agenda is planned to the minute and the arithmetic is verified by script, not by eye.

One decision still settling Session length. Sessions run 75 minutes, twice a week — 18 × 75 = 22½ hours. This is the lowest contact time the programme has used, and the practice that no longer fits is set as homework — on the three paired sessions, which cover two topics each, that means the Required tier of both notebooks, 30–40 minutes, and the Extra tier is not asked for on top. Nothing new is ever introduced at home: every task is already in the notebook. Teachers are told this at enrolment, not in week three. Once a group has settled in, the rhythm may change — shorter or longer sessions, or a different number per week (an earlier plan had three shorter sessions per week). The topics and deliverables would not change. Tools. Anaconda, Jupyter and VS Code, with Google Colab and Thonny under discussion as a lighter alternative that would remove the installation problem entirely. Current materials assume Anaconda and VS Code.

| Week | Sessions | Topics | What the participant can do by the end of it | Assessment |
| --- | --- | --- | --- | --- |
| 1 | 1–2 | 1–3 | It runs on my laptop, and I know what a value is |  |
| 2 | 3–4 | 4–5 | I can name things |  |
| 3 | 5–6 | 6–7 | A whole class in one list |  |
| 4 | 7–8 | 8–10 | I can find one student, and the computer decides |  |
| 5 | 9–10 | 11–13 | One loop marks thirty students | Midpoint, after session 10 |
| 6 | 11–12 | 14–15 | I can report on the whole class |  |
| 7 | 13–14 | 16–17 | I write the calculation once and use it everywhere | Trial class with real pupils |
| 8 | 15–16 | 18–21 | It is a program now, not a notebook |  |
| 9 | 17–18 | 22–24 | It has my class in it, it saves, and I showed it to someone | Final assessment, in session 18 |

Weeks 4 and 5 are the centre of the course — where the first discovery sessions pay off and, in session 9, a loop first does thirty students' work. If the calendar slips, those weeks are protected.

## The shape of a session

Two shapes are used. A standard session is a recap, twelve minutes of teaching, the notebook's examples run together, the exercises, then a short retrospective. A discovery session splits the teaching in two — seven minutes introducing the task, the long way done by hand, nine minutes introducing the tool, then the same task again with it, and a comparison.

Teaching never exceeds 12 minutes in one block. The rest of a session goes to hands-on work and to the second half of the discovery sessions, which is where the method lives. Hands-on is never less than half of a session.

## Remote delivery

The course is taught over Google Meet with screen sharing, in groups of four to eight. Fewer than four and there is no discussion; more than eight and the instructor cannot check on everyone during hands-on work, so the people who are quietly stuck stay stuck.

| Remote delivery | Effect |
| --- | --- |
| Removes the worst day-one risk | In a room, a whole group downloading 1 GB over one school connection would have cost a session. Each teacher now installs at home, on their own connection, before session 1 |
| Removes the best mitigation | An instructor cannot walk over and look at a screen. Everything that was a thirty-second fix becomes a conversation with a beginner who often cannot describe what they are seeing |
| The substitute | Google Meet can now display every participant's shared screen at once, with switching between them. Screens stay shared through hands-on work — the remote equivalent of walking between desks — and with 4–8 people the instructor checks in on each one by name |
| Requires of each teacher | Their own laptop for the whole course, and a connection that holds a 75-minute video call with screen sharing. A webcam is wanted but not required |

Every requirement is asked on an enrolment questionnaire before a group is formed — days available, connection, webcam, familiarity with video calls, known technical problems, and the laptop's memory and free disk. Several of the answers decide whether a teacher can take part at all, and acting on them early is what replaces the instructor's physical presence.

## Between sessions — homework, and it is required

Two sessions a week of 75 minutes is 22½ hours in the room, against 30 on the original three-a-week plan. Nothing was removed from the course; what no longer fits is done at home, and it is required rather than optional.

| After a session covering… | What is done at home | How long |
| --- | --- | --- |
| one topic, or the setup session — thirteen of the eighteen | the extra questions | 15–20 min |
| two topics, taught together — three of the eighteen | the main questions for both notebooks | 30–40 min |
| the transition and project sessions — the other two | nothing | — |

What homework is, and what it is not Every question is already printed in the notebook the session used, in the same three tiers and the same form as the work done together. Nothing new is ever introduced at home. The hardest tier is never set as homework. Those questions exist for the fastest one or two in a room, and only in the room. Every session opens by going through the last one's homework, so it is checked rather than assumed — and a participant falling behind is visible in week two rather than week six. Teachers are told this before they enrol. A course that asks for three evenings a week when it advertised two is how a cohort is lost.

The assessments are separate sittings and consume no session time.

# 5.  Curriculum — the grade-10 course

Topics are taught in the order a beginner can absorb them: printing, types, variables, conditions, loops, functions. Lists and dictionaries are placed where they solve a problem the participant has just met, rather than where a textbook would put them. The course teaches 24 topics across 18 sessions of 75 minutes: a topic is one notebook and one idea, a session is 75 minutes in a room. D marks a topic taught as a discovery session, T the transition to real files, P the project phase.

| Topic |  | Title | What the participant has at the end |
| --- | --- | --- | --- |
| 1 |  | Install everything and run your first line | Six green setup checks, and a line printed by a machine they set up themselves |
| 2 |  | Printing properly | A four-line class register header |
| 3 |  | Four kinds of value | Each type shown, and why "2" + 2 fails |
| 4 |  | Changing type, and asking a question | A cell that takes a grade and prints it plus one |
| 5 |  | Giving a value a name | One student's row printed from named values |
| 6 | D | A register for the whole class | Their class as one list, written both ways and compared |
| 7 |  | Working with the register, and two near-relatives | A sorted class list, plus the same names as a tuple and a set |
| 8 | D | Finding one student | Their class as name-to-grade, and a note on what went wrong before |
| 9 |  | The first decision | Pass or fail, on their own school's pass mark |
| 10 |  | More than two outcomes | A grade sorted into four named bands |
| 11 | D | Marking the whole class | The whole register marked, in four lines |
| 12 |  | Counting and totalling | Their own class average, computed |
| 13 |  | Loops that decide | Who failed, how many passed, the highest grade |
| 14 |  | Reports from the register | A printed register line per student, columns aligned |
| 15 |  | Several grades per student | A report card per student with three grades each |
| 16 |  | Entering grades one by one | A loop that collects grades until told to stop |
| 17 | D | An average on every card | The calculation written once, called four times |
| 18 |  | Sending an answer back | Four working grade functions that return values |
| 19 |  | The register, assembled (no new syntax) | The complete register program in one notebook |
| 20 | T | Leaving the notebook | python grades.py running in a terminal |
| 21 | T | Two files that each do one thing | A working `python main.py`, confirmed individually |
| 22 | D | Keeping it after you close it | Their own class in a file, loaded and saved back |
| 23 | P | Make it yours | One feature of their own design, working |
| 24 | P | Finish and show | A colleague runs their program from their notes alone |

Topics 1–19 use Jupyter notebooks; topics 20–24 use plain Python files with a written guide beside them, because by then the participants are running a terminal. Topic 19 doubles as the catch-up — nothing new arrives, so anyone who has fallen behind has time to recover.

## Alignment with the state curriculum

Our teachers must be able to deliver «ԱԲ սերունդ»: Computer Science in Python, approved by order 1875 of 09.09.2026 — a 24-topic, 193-hour curriculum for pupils in grades 10 and 11. Our programme is not a compressed copy of it; it is the preparation that makes delivering it possible.

| State curriculum | Pupil hours | Covered by |
| --- | --- | --- |
| Grade 10 · S1 — fundamentals (topics 1–12) | 60 | the grade-10 course, topics 1–11 |
| Grade 10 · S2 — intermediate (topics 13–17) | 65 | Part 1 for functions and files; Part 2 for advanced functions and recursion |
| Grade 11 · S1 — classes and inheritance (18–20) | 30 | Part 2, stage 5 |
| Grade 11 · S2 — libraries, debugging, git (21–24) | 38 | Part 2, stage 6. Git remains out of scope pending Part 1's result |

A teacher finishing Part 1 can deliver grade 10 semester 1 outright, and the first two topics of semester 2 — functions and files. Two orderings differ from the state document deliberately: we teach conditions before loops, and every data type before both, because our discovery sequence depends on having something worth looping over. Recursion stays before classes, as the state curriculum has it.

# 6.  Expected results

## What every participant leaves with

A runnable Python program, in their own folder, made of three files they typed themselves. One command — python main.py — opens their class, shows who passed, lists who did not, corrects a grade, and saves. Two of the three exist by the end of session 16; the third arrives in session 17, when files are taught.

| File | Its one job | What it deliberately does not know |
| --- | --- | --- |
| grades.py | Every number you might want to change, and the calculations: average, highest, pass or fail | Nothing about files, and nothing about printing |
| storage.py | Reads the class from a file and writes it back | Nothing about grades or what they mean |
| main.py | Asks the teacher what they want, and prints | It does no calculating of its own |

The separation is itself an outcome: because grades.py does not import storage.py, a participant can test the calculations without having a data file. When an answer looks wrong they can ask which half is wrong — the calculation or the display — and halve the search. That habit is the most transferable thing in the course.

## The checkpoints worth watching

| By the end of | Every participant has |
| --- | --- |
| Session 9 | The whole register marked in four lines, proved by adding students without touching the loop |
| Session 14 | A calculation written once and used in four places, with a change proved in a single edit |
| Session 16 | A working `python main.py` — confirmed individually, per person, before they leave the call. Everything after this session assumes it |
| Session 18 | A documented program a colleague ran unaided, and a 90-second demonstration given aloud |

## Skills and habits

Programming. print · the four value types · input · variables and formatted strings · if / elif / else · lists · for and range · while · dictionaries · functions and return · reading and writing files · modules and running a program from a terminal.

Habits that outlast the syntax, and what we most want to survive the course: if a number or a piece of code appears more than once, give it a name; when a result is wrong, ask which half is wrong before changing anything; and an error message is a sentence telling you what to fix, not a judgement.

What this course does not produce It does not produce programmers, and it does not produce people who can solve algorithmic problems. That is the next course, and only if this one works. A participant finishing this programme can write simple, working, useful code and read an error message. Saying so clearly now is what makes the measurement in section 8 honest.

# 7.  Scope and assessment

## What is deliberately excluded

The exclusion list matters as much as the syllabus. Classes, recursion, comprehensions, `lambda`, generators, regular expressions, type hints, decorators, web frameworks and databases are all out, along with package installation and virtual environments — which removes the most common way a beginner's setup breaks between sessions. Error handling is one safeguard at the outermost edge of the finished program, so an unexpected failure shows a sentence rather than ten lines of red text.

Each would cost roughly fifteen minutes and buy a teacher nothing in the program they are going to write. Most of them are Part 2's material. Before anything is added back, one question has to be answered: which line of the finished gradebook needs it?

## Differentiation within a session

In a group of four to eight, at least one or two finish early in every session, so each notebook carries three tiers: 3–4 required tasks sized so nobody leaves with unfinished work, 3–4 extra tasks for whoever has eight minutes to spare, and 1–2 challenges for the fastest. Extra tasks use only what has already been taught — wider, not further ahead. Running out of work is how a competent participant concludes a course is beneath them.

## Assessment

The assessments are being redesigned. The previous three sittings — a diagnostic, a midpoint and a final practical — were withdrawn on 16 October 2026. Two take their place: a midpoint after session 10 and a final assessment in session 18, both outside session time, under the decision rule in section 8.

Two rules hold whatever their content. The result is simply the share of tasks done — a task is done when the code runs and does what was asked, with no points and no partial credit. No help is given during a sitting: each participant completes the tasks alone. Nobody leaves at the midpoint: only the final assessment decides who continues (section 8).

# 8.  How success will be measured

## The decision rule

Part 1 succeeds or fails on one question: can they code? The thresholds were agreed with our partners on 15 October 2026, before the first session rather than after it. They are set at two levels: each teacher, then the group. Part 1 cannot be repeated: a teacher who does not continue after the final assessment leaves the programme.

### Each teacher — the two exams that count

The percentage is the share of the exam's tasks done. The rule below is agreed; the assessments it applies to are being redesigned (section 7).

| Tasks passed correctly | At the midpoint (after session 10) | At the final assessment (session 18) |
| --- | --- | --- |
| More than 85% | On track. Continues unconditionally | Pass. Continues to Part 2 |
| 70% to 85% | Probation. Continues; the teacher is told exactly where the problem is, and the method is adjusted for them in the sessions that remain | Individual review. The team looks at the teacher's work as a whole and decides whether they continue to Part 2 or leave |
| Less than 70% | Probation, with the highest priority | Leaves the programme |

Nobody leaves at the midpoint. A teacher under 85% continues on probation through the second month: they know exactly what their own problem is while there is still time to fix it, and the final assessment decides, on the same bands as everyone else. The midpoint also tells us where to adjust the course. Its bar is that a teacher can write code with every topic taught so far, with no algorithmic difficulty.

### The whole course — the decision rule

| Result | Meaning | What happens next |
| --- | --- | --- |
| More than 80% of teachers pass | Success | Continue to Part 2 (section 12) |
| 70% to 80% | Inconclusive | The method is neither proved nor refuted. Adjust Part 1 and run it with a new cohort before committing to Part 2 |
| Less than 70% of teachers pass | Failure | Return to the conventional approach, informed by where it broke |

Here a teacher passes if they meet both halves of "can code" below: above 85% on the final assessment, and a working program at the hard gate. A teacher in the 70–85% band whom the review lets continue goes on to Part 2, but is reported separately rather than counted as a pass, so that the figure measures the method and not the review.

The middle band is not a hedge. It is the most likely outcome of a first run of anything, and deciding in advance what we do with it stops the result being argued into whichever camp someone already preferred.

### What "can code" means, in a way that can be counted

A participant can code if, unaided, they can write a working program using the constructs the course taught — variables, conditions, lists, loops, dictionaries and functions. That is judged from two artefacts the course already produces, both pass or fail:

They left session 16 with a working python main.py, confirmed individually while sharing their screen.

They did more than 85% of the final assessment's tasks. Those tasks require writing code from a blank cell.

Meeting both is a pass. Meeting only one is not a pass and goes to the individual review. Problem-solving is not part of this judgement: Part 1 does not teach it, and Part 2's benchmark measures it (section 12).

⚠ One thing we would ask you to agree before the first cohort Groups are four to eight. In a group of four or five, "more than 80%" still means every single participant — 4 of 4, 5 of 5. In a group of six, 5 of 6 is success and 4 of 6 is failure, with no middle band at all. One teacher whose laptop dies in week six can decide a small group's result on their own. So we propose two things: judge the criterion across all cohorts pooled, not per group — four groups of six is 24 people, where a percentage means something — and record withdrawals separately from failures, since a teacher reassigned by their school in week two has not failed to learn to code. Neither weakens the bar. They stop it being decided by one broken laptop.

## Trial classes with real pupils — a second criterion

Each teacher teaches real pupils during the programme: one or two coding trial lessons in Part 1, the first in the middle of the second month (around week 7), and two lessons on theoretical material in Part 2. By week 7 a teacher has covered values, variables, lists, dictionaries, conditions and loops — enough for a first coding lesson. The trial classes measure something none of the exams can: whether they can teach what they can code. Those are different abilities, and a teacher can have either without the other.

Nothing in the written assessments would detect a teacher who writes correct code and cannot explain it to a fifteen-year-old — and that teacher cannot deliver the state curriculum, which is what the whole programme is for. The trial classes are reported separately from the coding criterion and are not averaged with it.

Four things are recorded, kept deliberately light because a first lesson taught by a nervous adult is not a performance review: did the lesson happen and finish; did the pupils run code themselves or did the teacher demonstrate throughout; could the teacher read a pupil's error message and act on it live; and one sentence from the teacher on what surprised them. The third is the most diagnostic — it is the skill our course drills from topic 2 onward, and if it holds up in front of a class, the method transferred.

## The final assessment also decides who continues

A gate, announced in advance Teachers above 85% continue to Part 2. Those between 70% and 85% are reviewed individually, and the team decides whether they continue. Those under 70% leave the programme — Part 1 is not repeated. This makes the last assessment consequential for the individual, so it is announced before the course starts — in the recruitment text and at enrolment. People behave differently when they know, and discovering it afterwards would be unfair and would spoil the measurement. Not continuing is not a judgement on the teacher. At 22½ hours in the room, with mixed laptops and a remote room, the likeliest reasons are time, equipment and attendance — so why someone did not meet the bar is recorded, not just that they did not.

## The checkpoints along the way

Results during the course change what the instructor does next, and they come from artefacts the course already produces. Session 1: can each participant run a cell on their own. The midpoint: do they write a loop, or still repeat themselves — the first real evidence for or against the method. Session 16: does python main.py run, confirmed individually while they share their screen. Attendance is recorded throughout, because below a certain point nothing else is interpretable.

Please note when reading our final report Target numbers should be set jointly before the first session. A target chosen afterwards is not a target.

# 9.  Risks

One risk really matters: that after Part 1 teachers still do not feel comfortable writing code. Everything else below is a practical matter with a plan already in place.

## The approach itself

| Risk | What we do about it |
| --- | --- |
| Teachers may still not feel comfortable coding after Part 1. This is the risk that matters | It is exactly what the course measures: the midpoint shows it a month early, while the method can still be adjusted for each teacher, and the hard gate and the final assessment confirm it (section 8) |
| Problem-solving comes later. Part 1 builds fluency; algorithmic problems are Part 2's work | Part 2 is where it is taught, and the benchmark measures it (section 12) |
| Some participants may expect more explanation. The first half of a discovery session is deliberately hands-on | Every discovery session resolves its own difficulty, and the shortcut is promised in writing before the long half starts |
| The time is compact — 22½ hours, in 75-minute pieces, for working teachers | The scope is deliberately focused, and homework only repeats the session's own exercises |

## Delivery

Practical matters of running a remote course, each with a plan already in place.

| Point to manage | What we do |
| --- | --- |
| The ~1 GB software download, done by each teacher at home | Setup instructions sent three days early, with a reply confirming the setup check is green |
| Remote support. A quick fix in a room takes a little longer over a call | All screens shared during hands-on work, with Meet showing every participant at once; each person checked on by name; groups capped at eight so that is possible |
| Laptops that block software installation, or lack the ~5 GB needed | Confirmed with schools, and asked on the enrolment form, before anyone is admitted. A browser-based fallback exists for topics 1–19 (sessions 1–15) |
| The editor's interpreter picker, a common beginner slip | Only one choice is ever present; a callout in topics 1 and 2; the setup script reports which Python is running |
| Missed sessions — twice a week for nine weeks, on top of a teaching job | Every topic is self-contained; worked solutions published after each session; topic 19 is a catch-up with nothing new in it; every session starts with a recap |

The comparison we would ask you to make The conventional approach has two years behind it without the result we wanted. This approach has an argument behind it, a defined measurement and a decision point. We believe it gives teachers a real chance to become comfortable coding, and the measurement will show it.

# 10.  Requirements, cost and current status

| Per participant | Their own laptop for the whole course — Windows or macOS, about 5 GB free, and permission to install software |
| --- | --- |
| Connection | Good enough for a 75-minute video call with screen sharing, twice a week. This is the one requirement that most often needs solving before a teacher can start |
| Webcam | Wanted, not required. Without one the instructor loses the clearest signal that someone is stuck |
| Software | Anaconda and VS Code, both free. Two installations before session 1 and nothing afterwards; the course uses only Python's standard library |
| Not needed | No GPU, no server, no accounts, no API keys, no paid service of any kind |
| Staffing | One instructor per group of 4–8 |
| Cost | Zero. The only material cost is instructor time |

## Screening before a group is formed

Because the course is remote, the requirements above are asked and acted on before enrolment, not discovered in week one. Every teacher answers six questions: how many days a week they can commit, whether their connection is sufficient, whether they have a webcam, whether they can use Zoom or Google Meet, any technical problem worth knowing about, and their laptop's memory and free disk space.

The answers decide group composition — teachers who can commit two days a week cannot be mixed with those committing three — and they surface the cases that need solving first: a locked-down school laptop, a shared family machine, a connection that will not hold a call. This screening is what replaces the instructor's physical presence, and it is the single cheapest risk reduction available to a remote course.

## Verified by automated checks

All Part 1 materials are written. Four scripts run against them, and all currently pass: every session agenda sums exactly to its stated length; all 37 notebooks — lessons and worked solutions — execute cell by cell, in order, from a clean start; the language and dependency rules hold, with nothing outside Python's standard library imported anywhere; and the finished program runs end to end, with missing files, corrupt data and bad input each producing one actionable sentence rather than a technical traceback.

Every teaching cell designed to fail still raises exactly the error it claims. One that silently starts working is treated as a defect.

## Not yet verified — stated plainly

| Open item | What closes it |
| --- | --- |
| The Armenian terminology has not been reviewed by a native-speaker teacher | Every term is drawn from a single glossary, so a correction is one edit plus an automated sweep rather than a rewrite of nineteen files. Terms we are least sure of are already marked |
| The installation instructions have never been followed on a clean machine | Run once on a fresh Windows laptop and once on a fresh Mac, and timed, before the first session |
| Nothing has been taught to a real cohort | Every estimate of pacing here is a design estimate. The first cohort will find things we did not |
| The toolchain may change | Anaconda and VS Code are assumed throughout. Google Colab and Thonny are under discussion as a lighter alternative that would remove the installation problem — and with it the largest remaining delivery risk |
| Part 2's hours are not fixed yet | Part 2 runs for four months. Its weekly hours, and the principles of its assessment (section 12), are to be fixed and told to teachers before they enrol in Part 1, so that they agree to the whole programme and not only to its first half |
| Part 2's two exams are not set yet | The scope and thresholds of Part 2's midpoint and final exams follow from the benchmark sitting (section 12), which is therefore held before Part 1 starts. They are fixed and told to teachers before they enrol, with priority, so that training starts on time |

We would rather hand you a document that names these six than one that reads as finished.

# 11.  The grade-11 course

Since this dossier was last issued, a second course has been built and verified. It takes a teacher who has finished the course described above and prepares them to teach grade 11. It is the same length, the same shape and the same method: eighteen sessions of 75 minutes, twice a week for nine weeks, delivered remotely in groups of four to eight.

It is needed even by a teacher who already teaches grade 10. The grade-10 course touches some grade-11 material but does not concentrate on it, and it teaches no classes, inheritance or libraries at all. Those are the hardest parts of the grade-11 curriculum, and they need more practice than the grade-10 topics, not less.

|  | Grade-10 course | Grade-11 course |
| --- | --- | --- |
| Entry | None. Begins with installing software | The grade-10 course, and nothing beyond it |
| State topics | 1–14 | 15–22 and 24 |
| Spine | one class, in dictionaries | the whole school, as objects with statistics and charts |
| Teaches | print, types, variables, lists, dictionaries, conditions, loops, functions, files | classes, inheritance, NumPy, Matplotlib, pandas, recursion, debugging |
| Deliverable | a three-file gradebook over the teacher's own class | a five-file report tool over the teacher's own school file, with charts |
| Discovery sessions | 5 of 18 | 7 of 18 |
| Status | built and verified | built and verified |

## What changes between them, and why

Two rules invert, and both inversions are deliberate. The grade-10 course forbids classes and every third-party library, because they would let a participant skip the mechanics the course exists to build. The grade-11 course makes classes its centre and teaches three libraries, because those are state topics 18, 19, 15, 20 and 21, and a teacher has to be able to demonstrate them.

The order is preserved even so. The session that introduces NumPy first has participants write the standard-deviation formula out by hand. The session that introduces pandas first spends twenty-two lines parsing a file with the tools they already have. The library arrives as relief from work already done — never as a way to avoid understanding it.

What the two courses cover together 187 of the state curriculum's 193 pupil-hours, in 45 teacher-hours — two Part 1s of 22½ hours each. The six that remain are topic 23, version control, deliberately deferred until the rest of the subject is secure. A teacher who completes both can deliver grade 10 and grade 11 in full, apart from that topic.

## The grade-11 curriculum

The same shape as the first course: 24 topics across 18 sessions of 75 minutes. Seven of the eighteen are discovery sessions, marked D — two more than the first course, because almost everything here is a tool that replaces work the participant has just done by hand.

| Topic |  | Title | What the participant has at the end |
| --- | --- | --- | --- |
| 1 |  | The school, and what we are going to build | The school's real file open, and its average computed with what they already knew |
| 2 |  | Functions that bend | One report function called six ways, with defaults and named arguments |
| 3 |  | Sending back more than one answer | One pass over the register returning three figures at once |
| 4 | D | Six reports, six loops | Six lists the head teacher asked for, each on one line instead of four |
| 5 |  | Choosing while you build | A register labelled pass/fail in one line, and sorted by a rule of their own |
| 6 | D | A student is more than a grade | A Student class, after a misspelled dictionary key failed silently thirty lines away |
| 7 |  | The calculation moves inside | student.average() — the data and the thing that calculates it travelling together |
| 8 |  | A class full of students | A SchoolClass holding Student objects, and a School holding classes |
| 9 | D | Teachers as well as students | Person, Student and Teacher — the shared part written once, after copying it twice |
| 10 |  | One loop, many kinds | One loop printing the right line for every kind of person, with no if in it |
| 11 |  | The register, rewritten (no new syntax) | The first course's gradebook rebuilt with objects, side by side with the old one |
| 12 | D | The term's statistics | Mean, spread and extremes in four lines, after writing the spread formula out by hand |
| 13 |  | Whole arrays at once | Every grade changed at once, and failing marks selected without a loop |
| 14 | D | Show the head teacher | A real chart saved as a file, after drawing one with asterisks |
| 15 |  | The four charts a school asks for | Bar, histogram, line and grouped bar — and which question each answers |
| 16 | D | The school's own file | The file read correctly in one line, after twenty-two lines got it wrong |
| 17 |  | Filter, group, describe | Averages per class and per subject, without naming the classes in the code |
| 18 |  | The term report | File in, statistics and two charts out — all three libraries in one workflow |
| 19 | D | How deep does it go? | One recursive function that works at any depth, after loops ran out of levels |
| 20 |  | Where code comes from | pip, requirements.txt, environments and Colab — the only session needing internet |
| 21 |  | Wrong, with no error | A silent wrong answer found with a debugger, not by rereading |
| 22 | T | Five files that each do one thing | A working `python main.py`, confirmed individually |
| 23 | P | Make it yours | Their own school's data in, and one feature of their own design |
| 24 | P | Finish and show | A colleague runs their program from their notes alone |

## The grade-11 schedule

Identical in shape to the first course — two sessions a week for nine weeks, eighteen sessions of 75 minutes, 22½ hours in total, with homework between sessions drawn from tasks the notebooks already carry.

| Week | Sessions | Topics | What the participant can do by the end of it | Assessment |
| --- | --- | --- | --- | --- |
| 1 | 1–2 | 1–3 | My functions bend to what is asked of them |  |
| 2 | 3–4 | 4–5 | One line instead of six |  |
| 3 | 5–6 | 6–8 | A student is a thing, and the school is objects |  |
| 4 | 7–8 | 9–11 | They share what they have in common | Midpoint, after session 8 |
| 5 | 9–10 | 12–13 | I can measure a term |  |
| 6 | 11–12 | 14–15 | I can draw it |  |
| 7 | 13–14 | 16–18 | The school's own file goes in, a report comes out | Trial class with real pupils |
| 8 | 15–16 | 19–21 | Any depth, and I can find out why it is wrong |  |
| 9 | 17–18 | 22–24 | It is a program now, it runs on my school, and I showed it | Final assessment, in session 18 |

## How the grade-11 course is assessed

Being redesigned, on the same principle and with the same thresholds as the first course (section 8): a midpoint after session 8 and a final assessment in session 18. The midpoint matters more here — whether a participant can write a working class decides whether the libraries half of the course can start, and if the cohort is not there, the instruction is to spend a session on revision rather than press on.

## What a grade-11 participant finishes with

A five-file Python program — settings, people, loading, charts and an entry point — that reads their own school's grade file, prints the term's statistics by class and by subject, lists the pupils who need attention, and saves two charts as image files that can go straight into a report.

## Three gaps we are naming rather than hiding

Recursion is taught as mechanics only — walking a nested structure. Its algorithmic half, including the call stack and complexity, is Part 2 material. The build fails if the teaching material so much as names factorial or Fibonacci.

Topic 21 names six libraries and five environments. Three libraries are taught to the point of use. The rest are named once, in the final session, with what each one is and why a grade-11 teacher does not need it — because pupils will ask, and «that is difficult» is the wrong answer.

Neither course has been taught to a cohort. Everything above is a design claim, not a result.

# 12.  The decision point after two months

The programme is deliberately framed as an experiment with a decision at the end, and both outcomes are useful.

## The trial classes

One or two coding lessons in Part 1, the first around week 7, and two on theoretical material in Part 2. Each teacher teaches a lesson to real pupils. They are the only points in the programme that test the thing the programme exists for, and they inform the decision below alongside the coding criterion (section 8).

## If it works — Part 2, four months

Part 2 is outlined, not written. Building it before Part 1 reports would be assuming the answer to the question Part 1 exists to ask. The ordering below is not arbitrary: each stage depends on the one before it, and the first exists because Part 1 deliberately skipped it.

| Stage |  | Why here |
| --- | --- | --- |
| 1 | The theory we postponed — parameters in depth, *args/**kwargs, scope, comprehensions and lambda, nested loops and conditions, choosing between data structures, reading other people's code | Part 1 taught constructs as tools that solved a problem; it never explained how they work underneath. This stage is itself a test of the programme's claim — if theory now lands easily on top of two months of practice, the sequencing was right. State curriculum topic 16 |
| 2 | Recursion | Placed here for the same reason the state curriculum places it immediately after advanced functions: it is a fact about functions before it is a technique. Before classes, as the state curriculum has it. Topic 17 |
| 3 | Algorithmic tasks and problem-solving — problems with no given method; writing the approach in words before the code | The thing Part 1 was clearing the ground for. With the mechanics automatic, the whole of a participant's attention is free for the problem |
| 4 | Bigger projects — several times the size of Part 1's, built over weeks rather than sessions | Where structure starts to matter, and where a program becomes too big to hold in your head |
| 5 | Objects and classes, including inheritance | Deliberately late. Classes solve a problem a participant only feels once their programs are big enough to have it — which is why this follows stage 4. Topics 18–19 |
| 6 | Libraries and environments — pip, NumPy, Matplotlib, pandas, Colab and Kaggle | Together the largest block in the state curriculum, and the bridge into the Artificial Intelligence subject beside Python. This stage deliberately breaks Part 1's standard-library-only rule, which has done its job by then. Topics 15 and 21 |

Git and version control (state curriculum topic 23) stays out of scope and is revisited once Part 1 reports: if the cohort arrives at Part 2 comfortably, git and the remaining tooling go in; if not, the time is better spent elsewhere.

### How Part 2 is judged — the final milestone

The milestone is a real teacher's level, not a number we chose. Teachers who completed an earlier run of this training and now teach Python in a school are the benchmark — two or three teachers. Before Part 1 begins, they solve a set of beginner Python problems from LeetCode (Easy level), under the conditions Part 2 participants will meet at the end: the same problems, the same time limit, no internet and no AI. Their results are the milestone our teachers should reach by the end of the school year. It shows from the start where we are going and how far there is to go, and it sets the content, depth and thresholds of Part 2's exams.

| Step | What happens |
| --- | --- |
| Before Part 1 | The problem set is fixed. The benchmark teachers sit it; problems solved correctly and time taken are recorded for each of them |
| After the benchmark | The scope and thresholds of Part 2's two exams are set from their results, and teachers are told them before they enrol |
| During Part 2 | Similar problems are practised, and two trial lessons on theoretical material are taught. The exact benchmark problems are not practised, or the milestone would measure memory |
| Midway through Part 2 | A midpoint exam, on the same principle as Part 1's: on track, or probation for the rest of Part 2. Nobody leaves at it |
| End of Part 2, by the end of the school year | Participants sit the same set and are judged against the benchmark teachers' results: pass, individual review, or leave |

Like Part 1, Part 2 has a midpoint exam and a final exam, each with three outcomes. Their percentages are set once the benchmark has been sat and analysed, because before that there is nothing to set them from — which is why the benchmark comes before Part 1, not before Part 2.

A handful of teachers is a small baseline. Each benchmark result is recorded separately as well as together, and if they differ widely the report says so rather than averaging it away.

What Part 2 will show "Do it the long way, then get the tool" works for concrete mechanics. Stage 2 shows how well it suits algorithmic thinking, and the method adapts there if it needs to. Part 1's assessments measure mechanics. The way Part 2's final milestone is set is now agreed (above); the exact ranges of both Part 2 exams follow from the benchmark sitting.

## If it does not work

We return to the conventional approach, having learned something specific rather than having failed again in the same way. And we will know where it broke:

| Where it broke | What that tells us |
| --- | --- |
| At the mechanics — they still cannot code after 22½ hours | The time budget is wrong, not the theory. A longer course on the same method |
| At acceptance — they disliked the method and left | The theory is untested; the delivery needs rethinking |
| At transfer — they can code but cannot solve problems | The central assumption is wrong. This is the finding that would change our direction |

Either result is worth two months A third repeat of the approach that has not worked is not.

# Appendix — inventory of materials

Everything below exists today and is version-controlled. The counts are verified against the materials when this document is generated.

| Material | Grade 10 | Grade 11 | Audience |
| --- | --- | --- | --- |
| Lesson notebooks | 19 | 21 | Participant |
| Written guides | 5 | 3 | Participant |
| Worked solutions | 18 | 21 | Participant, after each session |
| Assessments | Being redesigned | Being redesigned | Participant / instructor |
| Reference program | 3 files | 5 files | Participant, from the transition session |
| Installation instructions, reference sheet, setup check | 3 | 3 | Participant |
| Instructor notes, curriculum, build specification | 3 | 3 | Instructor / organiser |
| Recruitment announcement, enrolment guidance | 2 | 2 | Prospective participants |
| Notebooks that must execute before any change is accepted | 43 | 48 | — automated |

Each course is held in the same version-controlled repository, and each has its own automated checks that must pass before a change is accepted: session arithmetic, execution of every notebook in order, the language and dependency rules, and the finished program running end to end. A further check runs across both courses and this document, confirming that every figure restated in more than one place still agrees. Nothing is reported as complete on the strength of inspection alone.

Programme dossier v3.6 · 16 October 2026 · Prepared for Fast Foundation. Figures in this document are generated from the programme materials and verified against them at the time of writing.